## Sheet1
Project Activity Parameters - Based on Work Packages
Sub-Task Category | Activity | Predecessor Activity* | Duration | Responsible Party** | Resources | Cost
Planning | Vehicle architecture conceptual design |  | 4 weeks | Executive Board |  |  |  | Partially Paid
Chassis | Design | P. Completion | 8 weeks | Phil Piper, Dante Archangeli |  | 3500 | Work | Paid
| Fabrication | Design | 12 weeks |  | Chassis Materials, A Fabricator, Money | 1000 | Material
Suspension | Tire selection | P. Completion | 2 weeks | Phil Piper | Access to TTC | 500 | TTO Access
| Research and development | P. Completion | 10 weeks |  | Tire Selection | 2148 | Tires
| Obtain Components | R and D | 2 weeks |  | Money | ??? | Springs/Dampers
| Fabrication | R and D | 2 weeks |  | Machine Shop Acces, Welding Team | ??? | Bearings
| Install | Fabrication | 1 week |  | Car Time | ??? | Raw Material
Low Voltage | Circuit diagram | P. Completion | 3 weeks | Phil Piper |  | ??? | PCBS
| Wiring diagram | Circuit Diagram | 2 weeks | Eli |  | ??? | Micro Controller
| Obtain Components | Wiring Diagram | 2 weeks | Anton | Money | ??? | DAQ
| Wiring Harness fabrication | Obtain Components | 4 weeks | Han | LV Components | ??? | Wiring and Other
| Harness Test | Fabrication | 2 weeks
| Install | Fabrication | 1 week |  | Car Time
High Voltage | Wiring Diagram | P. Completion | 5 weeks | Phil Piper |  | 5000 | Batteries
| Obtain Components | Wiring Diagram | 1 week | Taha | Money | ??? | Accumulator (Non Batteries
| Test batteries | Obtain Componenets | 2 weeks |  | Batteries | 3900 | Motor
| First Battery Stack fabrication | Battery Test | 2 weeks |  | Batteries, Machine Shop Access | 3200 | Motor Controller
| All Stacks fabrication | First Stack Fabrication | 2 weeks |  | Batteries, Machine Shop Access | 153.5 | Poron, Neoprene, Aluminum for heat spreaders
| Accumulator Box fabrication | Accumulator Design | 3 weeks |  | Machine Shop Access, Protocase Sponsorship
| Accumulator Test | Accumulator Box Design | 2 weels
| Install | Fabrication | 1 week |  | Car Time
Impact Attenuator | Design | P. Completion | 2 weeks | Claire Mallon |  | 100
| Obtain Components | Design | 1 week |  | Money
| Fabrication | Design | 1 week |  | Extra material from chassis, Machine shop access, Welding Team
| Test | Fabrication | 1 week |  | Extra IA device
| Install | Fabrication | 1 week |  | Car Time
Firewall | Design | P. Completion | 2 weeks | Jordan Gardner |  | 80 | Aluminum
| Obtain Components | Design | 1 week |  | Money | 100 | Insulating rubber
| Fabrication | S. Design, Design | 2 weeks |  | Machine shop access
| Install | Fabrication | 1 week |  | Car Time
Seat | Design | P. Completion | 3 weeks | Jordan Gardner |  | 100 | Foam for Mold
| Obtain Components | Design | 1 week |  | Money | 150 | Foam Seat inserts
| Fabrication | F. Design, Design | 7 weeks |  | Composites Team, Extra people, Wood shop access | 50 | Other Materials
| Install | Fabrication | 1 week |  | Car Time
Body | Concept Creation | P. Completion | 4 weeks | Sida Tang | Graphic Designer | 0 | Carbon Fiber
| Design | F. and Se. Completition, Concept Creation | 4 weeks | Jordan Gardner |  | 150 | Epoxy
| Obtain Components | Design | 1 week | Tilman | Money | 300 | Foam
| Fabrication | Obtain Components | 6 weeks |  | Composites Team, Extra people, Wood shop access | 150 | Vacuum bagging Stuff
| Install | Fabrication | 1 week |  | Car Time | 50 | Dacron
Steering | Design | S. Design, P. Completion | 4 weeks | Yossi Kohrman-Glaser |  | 330 | Rack
| Obtain Components | Design | 1 week |  | Money | 140 | Universal
| Fabrication | Obtain Componenets | 4 weeks |  | Machine shop access, Welding Team | 153 | Raw Materials
| Install | Fabrication | 1 week |  | Car Time | 180 | Steering Wheel
Transmission | Design | P. Completion | 4 weeks | Dante Archangeli |  | 300 | Steel and Aluminum Sheet
| Obtain Components | Design | 1 week |  | Money | 100 | Bearings
| Fabrication | Obtain Components | 3 weeks |  | Machine shop access, Welding Team | 1000 | Axles and tripos
| Install | Fabrication | 1 week |  | Car Time | 4000 | housing and hubs
Brakes | Brake selection | P. Completion | 1 week | Holden Lessie-Bole |  | 172 | Master Cyliner
| Design | Brake Slelection | 3 weeks |  |  | ??? | caliper and disk
| Obtain Components | Design | 1 week |  | Money | 84 | lines and hardware
| Fabrication | Obtain Components | 2 weeks |  | Machine shop access, Welding Team | 175 | Pedal Box hardware
| Install | Fabrication | 1 week |  | Car Time | 60 | Aluminum Stock
Coolant System | Design | B. Completion, P. Completion | 4 weeks | Craig Wojtala | Fluids/Heat transder Lab Access
| Obtain Components | Design | 1 week |  | Money | 300
| Testing | Obtain Components | 2 weeks |  | Fluids/Heat transder Lab Access
| Fabrication | Obtain Componenets | 2 weeks |  | Composites Team, Wood shop access
| Install | Fabrication | 1 week |  | Car Time
Total Cost | [5 empty] | 27625.5
* Predecessor Activity is prefaced with sub-task acronym if activity falls within a different sub-task
** A Party is responsible for the activities listed at, and below, their name