## Before Break
Priority | Due Date | Primary | Secondaries | External Co. | Task
1 | 2015-12-23 | Dante | Taha |  | Impact attenuator 0.049” rules question
2 | 2015-12-23 | Dante | Phil |  | Rebend battery box to flat shape
3 | 2015-12-23 | Dante, Phil, Taha |  |  | Finish chassis welds
3 | 2015-12-23 | Dante, Phil, Taha |  |  | Practice welding steel
1 | 2015-12-23 | Phil | Dante, Taha |  | Fab doc outline complete
1 | 2015-12-23 | Phil |  |  | Send winter break tasks to team
2 | 2015-12-23 | Phil | Dante, Taha |  | Tape Kapton to aluminum heat spreaders
2 | 2015-12-23 | Phil | Dante, Taha |  | Redo end plate CAM and CNC end plates

## During Break
Priority | Due Date | Primary | Secondaries | External Co. | Task
2 | 2015-01-13 | Dante | Taha, Miles |  | Drivetrain design and fab doc complete
2 | 2015-01-01 | Dante | Taha |  | Research and order 6 point safety harness
2 | 2015-01-01 | Dante | Taha |  | Drivetrain raw materials ordered
3 | 2015-01-13 | Dante | Phil |  | Cooling design and fab doc complete
3 | 2015-01-01 | Dante | Phil |  | Cooling raw materials ordered
100 | 2015-01-13 | Dante | Phil |  | Redesign chassis with 10” in mind
2 | 2015-01-13 | Holden | Dante |  | Pedal box design and fab doc complete
2 | 2015-01-01 | Holden | Dante, Taha |  | Pedal box raw materials ordered
2 | 2015-01-13 | Jordan | Josh |  | Seat design and fab doc complete
2 | 2015-01-01 | Jordan | Josh, Taha |  | Seat raw materials ordered
2 | 2015-01-13 | Josh | Jordan |  | Firewall design and fab doc complete
2 | 2015-01-01 | Josh | Jordan, Taha |  | Firewall raw materials ordered
2 | 2015-01-13 | Miles | Phil |  | Dashboard design and fab doc complete
2 | 2015-01-13 | Miles | Phil |  | Steering wheel design and fab doc complete
2 | 2015-01-01 | Miles | Taha |  | Dashboard raw materials ordered
2 | 2015-01-01 | Miles | Taha |  | Steering wheel raw materials ordered
1 | 2015-01-13 | Phil |  |  | Accumulator fab doc complete
1 | 2015-01-13 | Phil |  |  | Motor controller cover design and fab doc complete
1 | 2015-01-01 | Phil | Taha |  | Accumulator materials ordered
2 | 2015-12-28 | Phil |  | Amphenol | Get HVD/SMD delivery date
2 | 2015-12-28 | Phil | Taha | Sikorsky | Get min corner radii and send finalized rear upright
2 | 2015-12-28 | Phil |  | TE Connectivity | Get 3 phase disconnect delivery date
2 | 2015-01-13 | Phil |  |  | Front upright design, CAM, and fab doc complete
2 | 2015-01-13 | Phil | Eli, Anton |  | LV wiring diagram complete
2 | 2015-01-13 | Phil |  |  | Suspension design and fab doc complete
2 | 2015-01-13 | Phil | Yossi |  | Steering design and fab doc complete
2 | 2015-01-01 | Phil | Taha |  | Wax blocks for front upright practice cuts ordered
2 | 2015-01-01 | Phil | Eli, Anton |  | LV circuit diagram complete
2 | 2015-01-01 | Phil | Taha |  | Suspension raw materials ordered
2 | 2015-01-01 | Phil | Yossi, Taha |  | Steering raw materials ordered
3 | 2015-01-01 | Phil | Taha | Hoosier | Strategize and submit tire order
3 | 2015-01-01 | Phil | Taha | Keizer | Strategize and submit wheel order
3 | 2015-01-01 | Phil |  |  | Get money from Grandpa Pipes
100 | 2015-01-13 | Phil |  |  | Redesign tires with 10” in mind
100 | 2015-01-13 | Phil |  |  | Redesign braking with 10” in mind
100 | 2015-01-13 | Phil |  |  | Redesign steering with 10” in mind
1 | 2015-01-13 | Taha | Yossi |  | Impact attenuator design and fab doc complete
1 | 2015-01-01 | Taha | Yossi |  | Impact attenuator raw materials ordered
1 |  | Taha | Phil, Dante |  | Weekly meetings
2 | 2015-01-03 | Taha | Phil | Sikorsky | Aluminum 7075-T6 for front uprights shipped
100 | 2015-01-13 | Taha | Phil |  | Redesign suspension with 10” in mind
1 | 2015-12-28 | Tyler | Phil | Stratasys | Get tab cover delivery date